## 📋 Cover
PortFolioPH
Offline/Online Portfolio Builder for Students
8-Sprint Agile Roadmap · 8 Weeks · 363 Total Hours
★ Developer | Mark Leannie Gacutno — 32 h/sprint (ALL coding + tech lead) = 256 h total
UX / QA | Tom Kyle B. Caballegan — 5-8 h/sprint (research, UI mockups, testing) ≈ 55 h total
Docs / Pres. | Rex Bernard G. Gabor — 5-8 h/sprint (documentation, proposals, presentation) ≈ 52 h total
Course | Web Application · MTh 4–5:30 PM · W 3–5 PM
Platform | Flutter Android · Offline-first SQLite · Firebase sync · PDF export
Duration | 8 Sprints × 1 Week = 8 Weeks (Mark 256h + Team 107h = 363h)
Deliverable | Signed Release APK + Capstone Presentation + Documentation
WORKBOOK SHEETS
📋 Cover | This page — project summary & navigation
📊 Dashboard | Sprint summary, hours budget, milestones
🏃 Sprint 1 | Core Setup & Architecture
🏃 Sprint 2 | Auth + Profile System
🏃 Sprint 3 | Projects CRUD + Gallery
🏃 Sprint 4 | Media Upload + Certificates
🏃 Sprint 5 | Achievements + Reflections
🏃 Sprint 6 | Resume Builder + PDF Export
🏃 Sprint 7 | Firebase Sync + Admin Panel
🏃 Sprint 8 | QA, Polish & APK Release
🗺 Master Tracker | Single source of truth — all sprints
📅 Class Schedule | 8 weeks mapped to sprints
📦 Tech Stack | Package manifest + verification checklist
📐 ERD | SQLite schema — 10 tables
🗂 Flutter Scaffold | Complete folder/file structure
✅ Day 1 Checklist | Sprint 1 kickoff checklist
📈 Metrics | Success KPIs + progress tracking

## 📊 Dashboard
PortFolioPH — Sprint Dashboard (8 Weeks)
Mark: 32h/sprint (ALL code) · Tom: 5-8h (UX/QA) · Rex: 5-8h (Docs) · 8 Weeks Total
Sprint | Week | Theme | Mark (Dev) | Tom (UX) | Rex (Docs) | Sprint Total | Demo Milestone | Dependencies | Status
1 | Wk 1 | Core Setup & Architecture | 32 | 6 | 6 | 44 | APK with splash + nav + offline DB | None | Not Started
2 | Wk 2 | Auth + Profile System | 32 | 7 | 6 | 45 | Full auth flow + dashboard | Sprint 1 | Not Started
3 | Wk 3 | Projects CRUD + Gallery | 32 | 6 | 6 | 44 | Add/edit/delete projects with images | Sprint 2 | Not Started
4 | Wk 4 | Media Upload + Certificates | 32 | 8 | 7 | 47 | Certificate CRUD + thumbnails | Sprint 3 | Not Started
5 | Wk 5 | Achievements + Reflections | 32 | 7 | 7 | 46 | Full portfolio data model complete | Sprint 4 | Not Started
6 | Wk 6 | Resume Builder + PDF Export | 32 | 8 | 7 | 47 | 3 PH templates + PDF export + share | Sprint 5 | Not Started
7 | Wk 7 | Firebase Sync + Admin | 32 | 6 | 6 | 44 | Online sync + admin panel + backup | Sprint 6 | Not Started
8 | Wk 8 | QA, Polish & APK Release | 32 | 7 | 7 | 46 | Signed APK + capstone presentation | Sprint 7 | Not Started
TOTAL | 8 Wks | ALL FEATURES |  |  |  |  | Production APK Submitted | Sequential | 8 Wks
★ MARK = 256 h total dev ¦ TOM = 55 h support ¦ REX = 52 h support ¦ GRAND TOTAL = 363 h

## 🏃 Sprint 1
Sprint 1: Core Setup & Architecture
Week 1 — Scaffold the entire Flutter project. Mark owns all code; Tom provides mockups; Rex starts proposal.
# | Task | Owner | Est Hrs | Notes | Status
★ MARK — Developer (32 h)
1 | Flutter project init: pubspec.yaml, all packages, android config | Mark | 3 | flutter create portfolioph --org com.portfolioph; Android-only | ⬜ Not Started
2 | Clean architecture folder structure — create ALL placeholder .dart files | Mark | 3 | See Flutter Scaffold sheet; models/ services/ providers/ screens/ widgets/ utils/ | ⬜ Not Started
3 | SQLite schema design — 10 tables, DatabaseService singleton | Mark | 6 | open(), close(), getDatabase(), runMigrations(); see ERD sheet | ⬜ Not Started
4 | AppConstants: colors, font sizes, padding, DB name/version | Mark | 2 | Zero magic numbers from Sprint 1 onward | ⬜ Not Started
5 | AppTheme: Material 3, brand colors, light/dark mode | Mark | 3 | ThemeData centrally defined; never hardcode colors in widgets | ⬜ Not Started
6 | AppRouter (GoRouter) — define ALL named routes upfront | Mark | 3 | Map every screen on day 1; auth redirect guard | ⬜ Not Started
7 | Bottom navigation scaffold + 5 placeholder tab screens | Mark | 3 | Tabs: Home, Portfolio, Resume, Skills, Profile | ⬜ Not Started
8 | Splash screen: logo + loading + session check → redirect | Mark | 3 | Check SharedPreferences for userId; redirect accordingly | ⬜ Not Started
9 | Android manifest: runtime permissions (storage, camera) | Mark | 2 | permission_handler; request at runtime not install time | ⬜ Not Started
10 | Git repo setup, branching strategy (main/develop/feature/*) | Mark | 2 | Push to GitHub; PRs required to merge to develop | ⬜ Not Started
11 | Run full Flutter app on physical Android device | Mark | 1 | Verify all packages resolve; splash → home nav works | ⬜ Not Started
12 | Sprint 1 integration test + code review | Mark | 1 | Ensure project compiles, routes work, DB opens | ⬜ Not Started
🔍 TOM KYLE — UX / QA (6 h)
1 | Research Philippine CV/portfolio app formats and student examples | Tom | 2 | Collect 5+ PH resume examples; document common sections | ⬜ Not Started
2 | Create low-fidelity UI wireframes for all 5 main tabs | Tom | 3 | Paper/Figma sketches; Mark reviews before Sprint 2 | ⬜ Not Started
3 | Test app on emulator — verify splash, navigation, no crashes | Tom | 1 | Install APK on emulator; report bugs to Mark | ⬜ Not Started
📝 REX BERNARD — Docs / Presentation (6 h)
1 | Create project proposal document: title, objectives, scope | Rex | 3 | LNU format; include team roles and timeline | ⬜ Not Started
2 | Write README.md: project overview, setup instructions, team | Rex | 2 | GitHub-ready README; include architecture diagram placeholder | ⬜ Not Started
3 | Set up shared Google Drive for all project documents | Rex | 1 | Folder structure: Proposals / Mockups / Meeting Notes / Assets | ⬜ Not Started
SPRINT TOTAL |  | ML + TK + RB | 44 | Mark 32h ¦ Tom 6h ¦ Rex 6h
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
Flutter/Android environment setup issues | High | Low | Block first 2 hrs for collective setup; flutter doctor on all machines
SQLite schema changes later break migrations | Medium | High | Finalize ERD sign-off before any code; version migrations
GoRouter learning curve | Low | Medium | Fallback to Navigator 2.0 if GoRouter >3 hrs stuck

## 🏃 Sprint 2
Sprint 2: Auth + Profile System
Week 2 — Offline PIN/biometric auth, profile CRUD. Students see their profile after login.
# | Task | Owner | Est Hrs | Notes | Status
★ MARK — Developer (32 h)
1 | UserModel: fromMap(), toMap(), copyWith() — immutable | Mark | 2 | Match ERD users table exactly; unit test roundtrip | ⬜ Not Started
2 | AuthService: register(name, email, password) → hashPassword + INSERT | Mark | 4 | SHA-256 via crypto pkg; parameterized SQL only | ⬜ Not Started
3 | AuthService: login(email, password) → verify hash → User | Mark | 3 | Throw AuthException on mismatch; log audit event | ⬜ Not Started
4 | AuthProvider (ChangeNotifier): authState, currentUser, isLoading | Mark | 3 | Wraps AuthService; notifyListeners() on every state change | ⬜ Not Started
5 | RegisterScreen: name, email, password, confirm password form | Mark | 3 | Real-time validation; disable button until valid | ⬜ Not Started
6 | LoginScreen: email + password form + 'Register' link | Mark | 3 | Calls AuthProvider.login(); SnackBar on error | ⬜ Not Started
7 | ProfileService: getProfile(userId), updateProfile(user) | Mark | 3 | Separate from AuthService (SRP) | ⬜ Not Started
8 | ProfileSetupScreen: avatar, bio, school, course, year level | Mark | 3 | image_picker for avatar; save path to users.avatar_path | ⬜ Not Started
9 | DashboardScreen: greeting + placeholder stat cards | Mark | 3 | Welcome {user.name}; cards: Projects (0), Achievements (0), etc. | ⬜ Not Started
10 | Session persistence: auto-login from SharedPreferences | Mark | 2 | On launch check userId → skip login if valid | ⬜ Not Started
11 | validators.dart + date_formatter.dart utility functions | Mark | 2 | validateEmail(), validatePassword(), formatDate() | ⬜ Not Started
12 | Sprint 2 integration: register → login → dashboard → logout | Mark | 1 | Full auth flow working on physical device | ⬜ Not Started
🔍 TOM KYLE — UX / QA (7 h)
1 | Create UI mockups for login, register, profile, dashboard screens | Tom | 3 | Material 3 style; match AppTheme brand colors | ⬜ Not Started
2 | Write 10 user testing scenarios for auth flow | Tom | 2 | Happy path + edge cases: wrong password, empty fields, etc. | ⬜ Not Started
3 | Research accessibility best practices for mobile auth forms | Tom | 2 | Font scaling, contrast ratios, screen reader labels | ⬜ Not Started
📝 REX BERNARD — Docs / Presentation (6 h)
1 | Document user registration flow (step-by-step with screenshots) | Rex | 3 | Include in capstone documentation chapter | ⬜ Not Started
2 | Write system architecture section for proposal | Rex | 2 | Architecture diagram: UI → Provider → Service → SQLite | ⬜ Not Started
3 | Meeting minutes for Sprint 2 planning + retrospective | Rex | 1 | Decisions, action items, blockers documented | ⬜ Not Started
SPRINT TOTAL |  | ML + TK + RB | 45 | Mark 32h ¦ Tom 7h ¦ Rex 6h
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
crypto package compatibility on Android API 21 | Low | Medium | Test SHA-256 on API 21 emulator in first coding session
image_picker crash on older Android | Medium | Medium | Wrap in try-catch; fallback to default avatar asset
Mark overloaded — 32h all coding | Medium | High | Strict task priorities; cut polish if behind schedule

## 🏃 Sprint 3
Sprint 3: Projects CRUD + Gallery
Week 3 — Full project add/edit/delete with multi-image upload and SQLite storage.
# | Task | Owner | Est Hrs | Notes | Status
★ MARK — Developer (32 h)
1 | ProjectModel: id, userId, title, desc, techStack, dates, tags | Mark | 2 | imageUrls stored as comma-separated local paths | ⬜ Not Started
2 | ProjectService: create, getAll, getById, update, delete, search | Mark | 5 | All queries WHERE user_id=?; parameterized SQL only | ⬜ Not Started
3 | ImageStorageService: saveImage(), deleteImage(), compressImage() | Mark | 4 | flutter_image_compress; max 500KB; max 5 images per project | ⬜ Not Started
4 | ProjectProvider (ChangeNotifier): projects list, loading, CRUD | Mark | 3 | Expose loading/error states; refresh list after every CRUD op | ⬜ Not Started
5 | ProjectsListScreen: ListView.builder + search bar + filter chips | Mark | 4 | LIMIT/OFFSET pagination from day 1; never fetchAll() | ⬜ Not Started
6 | AddEditProjectScreen: title, desc, tags, dates, tech stack, images | Mark | 5 | Same screen for add/edit; null projectId = add mode | ⬜ Not Started
7 | ProjectDetailScreen: full view + image carousel + edit/delete | Mark | 4 | ImageCarousel extracted as reusable widget | ⬜ Not Started
8 | Reusable widgets: PortfolioCard, EmptyStateWidget, LoadingWidget, TagChip | Mark | 3 | Parameterize via constructor; zero hardcoded strings | ⬜ Not Started
9 | file_utils.dart: getLocalPath(), generateUniqueFilename() | Mark | 1 | Relative paths stored; resolve absolute at runtime | ⬜ Not Started
10 | Sprint 3 end-to-end: add project with images → view → edit → delete | Mark | 1 | Full CRUD working on physical device | ⬜ Not Started
🔍 TOM KYLE — UX / QA (6 h)
1 | Research PH student project categories and tagging conventions | Tom | 2 | Suggest preset categories: Academic, Personal, Freelance, etc. | ⬜ Not Started
2 | UI mockups for project list, add/edit, detail screens | Tom | 2 | Card layouts, image carousel placement, filter bar | ⬜ Not Started
3 | Test all project CRUD operations — report bugs | Tom | 2 | Add 5 test projects with images; test search + delete | ⬜ Not Started
📝 REX BERNARD — Docs / Presentation (6 h)
1 | Document project module in capstone paper (data flow + UI) | Rex | 3 | Include screenshots, DB schema reference, code snippets | ⬜ Not Started
2 | Define data validation rules for project fields | Rex | 2 | Title max 100 chars, description max 2000, image max 5 | ⬜ Not Started
3 | Meeting minutes for Sprint 3 | Rex | 1 | Decisions, retrospective notes | ⬜ Not Started
SPRINT TOTAL |  | ML + TK + RB | 44 | Mark 32h ¦ Tom 6h ¦ Rex 6h
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
Local storage fills with uncompressed images | High | High | Enforce max 500KB via flutter_image_compress before saving
Slow list rendering with 50+ entries | Medium | Medium | LIMIT/OFFSET pagination from day 1
File path breaks after reinstall | Medium | High | Store relative paths; resolve absolute at runtime

## 🏃 Sprint 4
Sprint 4: Media Upload + Certificates
Week 4 — Image/document picker, certificate CRUD, and local media management.
# | Task | Owner | Est Hrs | Notes | Status
★ MARK — Developer (32 h)
1 | CertificateModel: id, userId, title, issuer, dates, filePath, type | Mark | 2 | type: Online ¦ Physical ¦ Award; filePath for scans | ⬜ Not Started
2 | CertificateService: full CRUD + filterByType() + search | Mark | 5 | Support: All / Online / Physical / Award filter tabs | ⬜ Not Started
3 | CertificateProvider (ChangeNotifier): filteredList by type | Mark | 2 | Consistent provider pattern matching ProjectProvider | ⬜ Not Started
4 | CertificatesListScreen: card view + filter tabs + search bar | Mark | 4 | Certificate card shows issuer + expiry badge | ⬜ Not Started
5 | AddEditCertificateScreen: form + document upload (image_picker + file_picker) | Mark | 4 | Allow JPG, PNG capture; graceful error if file too large | ⬜ Not Started
6 | MediaManagerService: unified image/doc picker + thumbnail generation | Mark | 4 | Central service for all file operations across modules | ⬜ Not Started
7 | Thumbnail generation: create 200px previews for gallery views | Mark | 3 | Cache thumbnails in app directory; delete with original | ⬜ Not Started
8 | Storage quota display: show used/available space in profile | Mark | 2 | Calculate folder sizes; warn if >100MB used | ⬜ Not Started
9 | SkillModel + SkillService basic CRUD (prep for Sprint 8) | Mark | 3 | category: Technical ¦ Soft Skill ¦ Language ¦ Tool; rating 1-5 | ⬜ Not Started
10 | Permission handling polish: camera, storage, file picker | Mark | 2 | Graceful denial handling; explain why permissions needed | ⬜ Not Started
11 | Sprint 4 integration test on physical device | Mark | 1 | Upload certificate scan → view thumbnail → filter by type | ⬜ Not Started
🔍 TOM KYLE — UX / QA (8 h)
1 | UI mockups for certificate screens + media picker flow | Tom | 3 | Include upload progress indicator, thumbnail grid layout | ⬜ Not Started
2 | Research Android file format support + storage permission changes | Tom | 2 | API 30+ scoped storage; document impact | ⬜ Not Started
3 | Test certificate upload flow on 2 Android versions | Tom | 3 | Test on API 26 and API 33; report permission issues | ⬜ Not Started
📝 REX BERNARD — Docs / Presentation (7 h)
1 | Document media upload module for capstone paper | Rex | 3 | File storage strategy, compression, permission flow | ⬜ Not Started
2 | Research file format standards for PH certificates | Rex | 2 | Common cert formats from TESDA, DICT, universities | ⬜ Not Started
3 | Update project proposal with progress report | Rex | 2 | Include screenshots of working Sprint 1-4 features | ⬜ Not Started
SPRINT TOTAL |  | ML + TK + RB | 47 | Mark 32h ¦ Tom 8h ¦ Rex 7h
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
File picker permissions differ on Android 11+ (scoped storage) | High | High | Test on API 30+ first; use SAF-compatible picker
Thumbnail generation slow on low-end devices | Medium | Medium | Generate async; show shimmer placeholder while loading
Storage space warnings ignored by user | Low | Medium | Force-show dialog at 80% quota; disable uploads at 95%

## 🏃 Sprint 5
Sprint 5: Achievements + Reflections
Week 5 — Achievements CRUD, reflections journal, and complete portfolio data model.
# | Task | Owner | Est Hrs | Notes | Status
★ MARK — Developer (32 h)
1 | AchievementModel: id, userId, title, desc, date, type, imagePath | Mark | 2 | type: Academic ¦ Extracurricular ¦ Competition ¦ Other | ⬜ Not Started
2 | AchievementService: full CRUD + searchByTitle() | Mark | 4 | Mirror ProjectService pattern for consistency | ⬜ Not Started
3 | AchievementProvider: expose filteredList by type | Mark | 2 | Consistent with Certificate/Project providers | ⬜ Not Started
4 | AchievementsListScreen + AddEditAchievementScreen | Mark | 5 | Reuse PortfolioCard widget; tag with achievement type chip | ⬜ Not Started
5 | ReflectionModel: id, userId, title, body, mood, tags, isPrivate, date | Mark | 2 | isPrivate=1 → hidden from PDF exports | ⬜ Not Started
6 | ReflectionService: full CRUD + searchByBody() (SQLite LIKE) | Mark | 4 | LIKE '%query%' search; FTS5 not guaranteed on all devices | ⬜ Not Started
7 | ReflectionProvider + ReflectionsListScreen + ReflectionEditorScreen | Mark | 5 | Editor: title + multiline body + mood picker + tags + private toggle | ⬜ Not Started
8 | PortfolioOverview tab: aggregate all modules with counts + recent | Mark | 4 | Show: X projects, Y certs, Z achievements, W reflections + recent 3 each | ⬜ Not Started
9 | SkillsTrackerScreen: categorized list + rating stars + add/edit modal | Mark | 3 | AnimatedContainer progress bars per skill (1-5) | ⬜ Not Started
10 | Sprint 5 full portfolio integration test | Mark | 1 | Add entries to all modules → see overview → search across all | ⬜ Not Started
🔍 TOM KYLE — UX / QA (7 h)
1 | Research PH student achievement types + common formats | Tom | 2 | Dean's list, org awards, hackathon certs — categorize all | ⬜ Not Started
2 | UI mockups for achievements list + reflection editor | Tom | 2 | Mood picker design; privacy toggle placement | ⬜ Not Started
3 | Test all 5 portfolio modules end-to-end; bug report | Tom | 3 | 10+ test entries across all modules; search + filter tests | ⬜ Not Started
📝 REX BERNARD — Docs / Presentation (7 h)
1 | Document achievements + reflections module for capstone | Rex | 3 | Data model diagrams, screenshots, user flow | ⬜ Not Started
2 | Research validation rules for achievement/reflection fields | Rex | 2 | Max lengths, required fields, date constraints | ⬜ Not Started
3 | Mid-project progress report for professor | Rex | 2 | 5 modules implemented; include metrics + screenshots | ⬜ Not Started
SPRINT TOTAL |  | ML + TK + RB | 46 | Mark 32h ¦ Tom 7h ¦ Rex 7h
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
SQLite LIKE search slow on large datasets | Medium | Medium | Index commonly searched columns; LIMIT results to 50
Reflection editor scope creep (rich text demands) | High | Medium | Plaintext ONLY this sprint; rich text = backlog
Portfolio overview query too many JOINs → slow | Medium | Medium | Denormalize counts in a stats cache; refresh on CRUD

## 🏃 Sprint 6
Sprint 6: Resume Builder + PDF Export
Week 6 — 3 Philippine CV templates, live preview, PDF generation, share functionality.
# | Task | Owner | Est Hrs | Notes | Status
★ MARK — Developer (32 h)
1 | ResumeModel: id, userId, templateId, customSections JSON, isDefault | Mark | 2 | Persist draft to SQLite; auto-save on every change | ⬜ Not Started
2 | ResumeDataService: mapPortfolioToResumeData(userId) | Mark | 4 | User selects which portfolio entries to include per section | ⬜ Not Started
3 | ResumeTemplateSimple widget — PH government/academic style | Mark | 3 | Sections: Personal Info, Objective, Education, Skills, Projects | ⬜ Not Started
4 | ResumeTemplateProfessional widget — corporate PH style | Mark | 3 | Header, Summary, Projects/Experience, Certs, Skills, References | ⬜ Not Started
5 | ResumeTemplateModern widget — fresh grad tech style | Mark | 3 | Two-column; skills as chips; accent color from AppTheme | ⬜ Not Started
6 | PdfService: generateResumePdf() — pdf package with TTF fonts | Mark | 5 | Register Roboto TTF FIRST to handle Filipino chars (ñ, etc.) | ⬜ Not Started
7 | PDF layout for all 3 templates (mirror Flutter widget structure) | Mark | 4 | pw.Page, pw.Column, pw.Text; test ñ, ü characters | ⬜ Not Started
8 | PdfExportScreen: preview (printing pkg) + save to Downloads + share | Mark | 3 | path_provider for Downloads; share_plus for Android share sheet | ⬜ Not Started
9 | ResumeBuilderScreen: live preview + section toggles + field overrides | Mark | 3 | Show/hide sections; edit summary inline; real-time re-render | ⬜ Not Started
10 | ExportHistoryService: log exports to audit table | Mark | 1 | SQLite export_history table; shown in Profile as 'My Exports' | ⬜ Not Started
11 | Sprint 6 end-to-end: select template → fill data → export PDF → share | Mark | 1 | PDF opens correctly on device; Filipino chars render | ⬜ Not Started
🔍 TOM KYLE — UX / QA (8 h)
1 | Design review of all 3 resume templates — color, spacing, typography | Tom | 3 | Compare with real PH hiring standards; suggest improvements | ⬜ Not Started
2 | Research Philippine CV format standards (DOLE, CHED guidelines) | Tom | 2 | 2×2 photo req, personal details placement, section order | ⬜ Not Started
3 | Test PDF export on 2 devices; verify formatting + file size | Tom | 3 | Check on low-end and mid-range Android phones | ⬜ Not Started
📝 REX BERNARD — Docs / Presentation (7 h)
1 | Document resume builder + PDF export for capstone paper | Rex | 3 | Template designs, PDF generation flow, export process | ⬜ Not Started
2 | Research PDF format best practices for mobile | Rex | 2 | File size targets, embeddability, print fidelity | ⬜ Not Started
3 | Write user manual draft for resume builder feature | Rex | 2 | Step-by-step guide with screenshots | ⬜ Not Started
SPRINT TOTAL |  | ML + TK + RB | 47 | Mark 32h ¦ Tom 8h ¦ Rex 7h
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
pdf package font issue with Filipino characters (ñ, special chars) | High | High | Register Roboto TTF in PdfService BEFORE building any layout
PDF with images = file size > 10 MB | Medium | Medium | Compress images before embedding; offer 'no images' export
printing pkg preview blank on some Android versions | Medium | Medium | Test on API 21, 28, 33; fallback to open-file intent

## 🏃 Sprint 7
Sprint 7: Firebase Sync + Admin Panel
Week 7 — Online sync with Firebase, admin dashboard, backup/restore, app security.
# | Task | Owner | Est Hrs | Notes | Status
★ MARK — Developer (32 h)
1 | Firebase project setup: FlutterFire init, Firestore rules, Auth | Mark | 3 | firebase_core, cloud_firestore, firebase_auth in pubspec | ⬜ Not Started
2 | SyncService: local-first merge strategy (SQLite → Firestore) | Mark | 5 | Conflict resolution: latest timestamp wins; queue offline changes | ⬜ Not Started
3 | Online auth: Firebase Auth email/password alongside offline PIN | Mark | 3 | Dual mode: offline-only PIN or online Firebase auth + sync | ⬜ Not Started
4 | Admin seeding: setup wizard on first launch (role='admin') | Mark | 2 | Admin user hardcoded or created via setup wizard | ⬜ Not Started
5 | AdminDashboard: total users, portfolios, exports, storage used | Mark | 4 | Read-only SQLite aggregates; auto-refresh on focus | ⬜ Not Started
6 | AdminUserListScreen: all students + portfolio counts + search | Mark | 3 | Tap student → view their portfolio (read-only admin view) | ⬜ Not Started
7 | BackupService: export full SQLite DB as .db file to Downloads | Mark | 3 | Include schema version in filename; for device migration | ⬜ Not Started
8 | RestoreService: import .db backup (schema version validation) | Mark | 3 | Validate version before import; warn on mismatch | ⬜ Not Started
9 | App PIN lock: 4-digit PIN, auto-lock after 5 min idle | Mark | 3 | Hashed PIN in SharedPreferences; 5 attempts → lock 30 min | ⬜ Not Started
10 | Input sanitization audit: review all SQL queries in all services | Mark | 2 | Zero string concatenation in SQL; all values via ? placeholders | ⬜ Not Started
11 | Sprint 7 integration: admin login → view students → backup → restore | Mark | 1 | Full admin + sync flow on physical device | ⬜ Not Started
🔍 TOM KYLE — UX / QA (6 h)
1 | Research Firebase free-tier limits (Firestore, Auth, Storage) | Tom | 2 | Document quotas; estimate usage for 50 students | ⬜ Not Started
2 | Test online sync: create offline → go online → verify sync | Tom | 2 | Multiple scenarios: conflict, partial upload, reconnect | ⬜ Not Started
3 | Test admin panel: view student data, backup/restore flow | Tom | 2 | Verify admin can't edit student data; read-only enforced | ⬜ Not Started
📝 REX BERNARD — Docs / Presentation (6 h)
1 | Document admin requirements + sync strategy for capstone | Rex | 3 | Admin capabilities, sync architecture, security measures | ⬜ Not Started
2 | Write data privacy section (PH Data Privacy Act compliance) | Rex | 2 | How student data is stored, encrypted, backed up | ⬜ Not Started
3 | Meeting notes + Sprint 7 retrospective documentation | Rex | 1 | Performance review, remaining work estimate | ⬜ Not Started
SPRINT TOTAL |  | ML + TK + RB | 44 | Mark 32h ¦ Tom 6h ¦ Rex 6h
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
Firebase quota exceeded during testing | Medium | High | Use Firebase Emulator for dev; limit reads in production
Offline → online conflict resolution bugs | High | High | Test conflict scenarios extensively; latest-timestamp-wins
DB restore corrupting live data | Medium | High | Restore to temp path → validate → swap files

## 🏃 Sprint 8
Sprint 8: QA, Polish & APK Release
Week 8 — Full testing, bug fixes, performance, signed APK, capstone presentation.
# | Task | Owner | Est Hrs | Notes | Status
★ MARK — Developer (32 h)
1 | Full regression test pass (manual end-to-end all user flows) | Mark | 4 | Test: register → all CRUD → export PDF → admin → sync | ⬜ Not Started
2 | Unit tests for all Services (target ≥80% service layer coverage) | Mark | 5 | mockito + flutter_test; happy path + error path each | ⬜ Not Started
3 | Widget tests: Login, Dashboard, ResumeBuilder key screens | Mark | 3 | pumpWidget + navigation test + state assertions | ⬜ Not Started
4 | Bug fix sprint: Critical → High → Medium (skip Low) | Mark | 5 | Triage all issues; document Low bugs in README 'Known Issues' | ⬜ Not Started
5 | Performance profiling: Flutter DevTools (fps, memory, DB queries) | Mark | 3 | Target: 60fps on mid-range; all DB queries < 50ms | ⬜ Not Started
6 | UI polish: loading skeletons, error states, empty states all screens | Mark | 3 | Shimmer loaders; micro-animations; consistent spacing | ⬜ Not Started
7 | Accessibility pass: semantics labels, contrast, font scaling | Mark | 2 | Demonstrates engineering maturity to capstone panel | ⬜ Not Started
8 | Keystore generation + app signing config | Mark | 2 | Store keystore + password in all 3 members' Google Drive | ⬜ Not Started
9 | flutter build apk --release --split-per-abi | Mark | 2 | Build arm64-v8a, armeabi-v7a; test on physical device | ⬜ Not Started
10 | Install + test release APK on 2 physical devices | Mark | 2 | Minimum: Android 8 (API 26) and Android 13 (API 33) | ⬜ Not Started
11 | Final code cleanup + comments + documentation in code | Mark | 1 | Remove debug prints, TODO comments, unused imports | ⬜ Not Started
🔍 TOM KYLE — UX / QA (7 h)
1 | Full QA testing on 2 physical devices — structured test cases | Tom | 3 | 50+ test cases across all modules; bug tracker updated | ⬜ Not Started
2 | Final UI review: typography, spacing, icon sizes all screens | Tom | 2 | Cross-check every screen against design mockups | ⬜ Not Started
3 | Help prepare capstone demo: run device, assist presentation | Tom | 2 | Backup device ready; know how to navigate app for Q&A | ⬜ Not Started
📝 REX BERNARD — Docs / Presentation (7 h)
1 | Complete capstone paper: all chapters finalized | Rex | 3 | Abstract, chapters 1-5, references, appendices | ⬜ Not Started
2 | Capstone presentation slides: 15-20 slides | Rex | 2 | Intro → problem → solution → demo → technical → conclusion | ⬜ Not Started
3 | Write 1-page user manual + README update | Rex | 1 | Quick-start guide; installation instructions | ⬜ Not Started
4 | Final retrospective document: lessons learned | Rex | 1 | What worked, what didn't, future roadmap | ⬜ Not Started
SPRINT TOTAL |  | ML + TK + RB | 46 | Mark 32h ¦ Tom 7h ¦ Rex 7h
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
Critical bugs discovered late in regression | High | High | Fix Critical + High only; document Medium/Low as known issues
Release APK > 50 MB | Medium | Medium | Enable R8/ProGuard; --split-per-abi to reduce size
Keystore file lost after project | High | High | Back up to ALL 3 members' personal Google Drive NOW

## 🗺 Master Tracker
PortFolioPH — Master Sprint Tracker
Mark = ALL code (32h/sprint) · Tom = UX/QA · Rex = Docs/Pres · Update weekly
Sprint | Week | Sprint Hrs | ★ Mark (Dev) | Tom (UX) | Rex (Docs) | Total Used | Progress % | Risk Level | Demo Deliverable | Notes
1 | Wk 1 | 44 | 32 | 6 | 6 |  |  | Low | Splash + nav + DB | Architecture established
2 | Wk 2 | 45 | 32 | 7 | 6 |  |  | Low | Auth flow + Dashboard | Login/register working
3 | Wk 3 | 44 | 32 | 6 | 6 |  |  | Medium | Projects CRUD | First real data entry
4 | Wk 4 | 47 | 32 | 8 | 7 |  |  | Medium | Certificates + thumbnails | Media pipeline done
5 | Wk 5 | 46 | 32 | 7 | 7 |  |  | Medium | Full portfolio done | All CRUD modules live
6 | Wk 6 | 47 | 32 | 8 | 7 |  |  | High | PDF export working | Feature complete
7 | Wk 7 | 44 | 32 | 6 | 6 |  |  | High | Admin + Firebase sync | Pre-release hardening
8 | Wk 8 | 46 | 32 | 7 | 7 |  |  | Low | Signed APK + capstone | Release ✔
TOTAL | 8 Wks | [7 empty] | Mark 256h + Team 107h = 363h

## 📅 Class Schedule
Class Time Integration — 8 Weeks
MTh 4–5:30 PM (3 hrs/session) · W 3–5 PM (2 hrs) · 7.5 hrs/week class time
Week | Day | Time | Activity | Hrs | Sprint | Deliverable
1 | Mon/Thu | 4–5:30 PM | Sprint 1: Project init, folder scaffold, DB schema session | 3 | S1 | Repo live + pubspec ready
1 | Wed | 3–5 PM | Sprint 1: AppRouter + AppTheme + splash screen | 2 | S1 | Navigation framework done
2 | Mon/Thu | 4–5:30 PM | Sprint 2: AuthService + login/register screens | 3 | S2 | Auth UI running
2 | Wed | 3–5 PM | Sprint 2: ProfileSetupScreen + DashboardScreen | 2 | S2 | Dashboard with greeting
3 | Mon/Thu | 4–5:30 PM | Sprint 3: ProjectService CRUD + AddEditProjectScreen | 3 | S3 | Project add/edit working
3 | Wed | 3–5 PM | Sprint 3: ImageStorageService + ProjectDetailScreen | 2 | S3 | Image carousel live
4 | Mon/Thu | 4–5:30 PM | Sprint 4: CertificateService + media picker + thumbnails | 3 | S4 | Certificate CRUD done
4 | Wed | 3–5 PM | Sprint 4: SkillModel CRUD + permission polish | 2 | S4 | Skills tracker started
5 | Mon/Thu | 4–5:30 PM | Sprint 5: AchievementService + ReflectionService CRUD | 3 | S5 | Achievement/reflection screens
5 | Wed | 3–5 PM | Sprint 5: PortfolioOverview aggregate + SkillsTrackerScreen | 2 | S5 | Full portfolio visible
6 | Mon/Thu | 4–5:30 PM | Sprint 6: PdfService + 3 resume template widgets | 3 | S6 | PDF generating
6 | Wed | 3–5 PM | Sprint 6: PdfExportScreen + share + ExportHistoryService | 2 | S6 | PDF export + share working
7 | Mon/Thu | 4–5:30 PM | Sprint 7: Firebase setup + SyncService + admin panel | 3 | S7 | Online sync working
7 | Wed | 3–5 PM | Sprint 7: BackupService + RestoreService + PIN lock | 2 | S7 | Backup/restore + security
8 | Mon/Thu | 4–5:30 PM | Sprint 8: Regression testing + bug fixes + APK build | 3 | S8 | Release APK built
8 | Wed | 3–5 PM | 🎓 CAPSTONE PRESENTATION + DEMO | 2 | Final | APK submitted ✔
⏱ Class: 7.5 hrs/wk × 8 wks = 60 hrs in-class ¦ Independent: 363 – 60 = 303 hrs outside class ¦ Mark codes 26+ hrs/wk independently

## 📦 Tech Stack
Technology Dependency Manifest
Verify ALL packages in Sprint 1 — install via pubspec.yaml on day 1
Package | Version | Used In | Risk | Verified | Notes
sqflite | ^2.3.0 | All Sprints | Low | [ ] | Core offline DB; test on Android API 21+
path_provider | ^2.1.0 | All Sprints | Low | [ ] | Required by sqflite for file paths
provider | ^6.1.0 | All Sprints | Low | [ ] | State management (ChangeNotifier)
go_router | ^13.2.0 | Sprint 1+ | Low | [ ] | Named routes; fallback to Navigator 2.0
shared_preferences | ^2.2.2 | Sprint 2+ | Low | [ ] | Session tokens + PIN hash storage
permission_handler | ^11.3.0 | Sprint 1+ | Medium | [ ] | Runtime permissions storage/camera
image_picker | ^1.0.7 | Sprint 3+ | Medium | [ ] | Camera + gallery; test on API 21–34
file_picker | ^6.1.1 | Sprint 4 | Medium | [ ] | Certificate doc uploads (JPG, PNG)
image_cropper | ^5.0.1 | Sprint 6 | Medium | [ ] | 2×2 photo crop for resume slot
pdf | ^3.10.8 | Sprint 6 | High | [ ] | Register TTF font EARLY — test Filipino chars
printing | ^5.12.0 | Sprint 6 | High | [ ] | PDF preview; test on API 21, 28, 33
share_plus | ^7.2.1 | Sprint 6+ | Low | [ ] | Android share sheet for PDF
firebase_core | ^2.27.0 | Sprint 7 | Medium | [ ] | Firebase initialization
cloud_firestore | ^4.15.0 | Sprint 7 | Medium | [ ] | Online sync for portfolios
firebase_auth | ^4.17.0 | Sprint 7 | Medium | [ ] | Online auth alongside offline PIN
shimmer | ^3.0.0 | Sprint 8 | Low | [ ] | Skeleton loaders on list screens
flutter_image_compress | ^2.0.0 | Sprint 3+ | Medium | [ ] | Max 500KB before saving images
mockito | ^5.4.4 | Sprint 8 | Low | [ ] | Unit test mocking
crypto | ^3.0.3 | Sprint 2+ | Low | [ ] | SHA-256 password hashing (local)
⚠ Add ALL packages to pubspec.yaml in Sprint 1 day 1. Run `flutter pub get` and test critical ones.

## 📐 ERD
SQLite Database Schema (ERD)
All tables use INTEGER PRIMARY KEY AUTOINCREMENT · FK enforced at app layer
TABLE: USERS
Student + admin accounts. role differentiates.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | — | Auto-increment
name | TEXT | NOT NULL |  | — | Full name
email | TEXT | NOT NULL | UNIQUE | — | Login identifier
password_hash | TEXT | NOT NULL |  | — | SHA-256 hashed
role | TEXT | NOT NULL |  | — | 'student' ¦ 'admin'
avatar_path | TEXT | NULL |  | — | Local file path
bio | TEXT | NULL |  | — | Short bio
school | TEXT | NULL |  | — | Institution name
year_level | TEXT | NULL |  | — | e.g. '3rd Year'
course | TEXT | NULL |  | — | e.g. 'BSIT'
pin_hash | TEXT | NULL |  | — | 4-digit PIN (SHA-256)
created_at | TEXT | NOT NULL |  | — | ISO 8601
updated_at | TEXT | NOT NULL |  | — | ISO 8601
TABLE: PROJECTS
Student portfolio projects.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
title | TEXT | NOT NULL |  | — | Project title
description | TEXT | NULL |  | — | Full description
tech_stack | TEXT | NULL |  | — | Comma-separated
tags | TEXT | NULL |  | — | JSON array string
start_date | TEXT | NULL |  | — | YYYY-MM-DD
end_date | TEXT | NULL |  | — | NULL if ongoing
project_url | TEXT | NULL |  | — | Optional link
created_at | TEXT | NOT NULL |  | —
updated_at | TEXT | NOT NULL |  | —
TABLE: PROJECT_IMAGES
One-to-many images per project (max 5).
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
project_id | INTEGER | NOT NULL | FK | projects.id | CASCADE DELETE
file_path | TEXT | NOT NULL |  | — | Local path
sort_order | INTEGER | NOT NULL |  | — | 0–4
created_at | TEXT | NOT NULL |  | —
TABLE: ACHIEVEMENTS
Awards, recognitions, academic achievements.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
title | TEXT | NOT NULL |  | —
description | TEXT | NULL |  | —
date_achieved | TEXT | NULL |  | — | YYYY-MM-DD
type | TEXT | NOT NULL |  | — | Academic¦Extracurricular¦Competition¦Other
image_path | TEXT | NULL |  | — | Optional photo
created_at | TEXT | NOT NULL |  | —
TABLE: CERTIFICATES
Digital/physical certificates with file attachment.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
title | TEXT | NOT NULL |  | —
issuer | TEXT | NOT NULL |  | — | Issuing org
issue_date | TEXT | NULL |  | — | YYYY-MM-DD
expiry_date | TEXT | NULL |  | — | NULL if no expiry
file_path | TEXT | NULL |  | — | Scan/photo path
type | TEXT | NOT NULL |  | — | Online¦Physical¦Award
created_at | TEXT | NOT NULL |  | —
TABLE: REFLECTIONS
Journal entries. isPrivate hides from PDF.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
title | TEXT | NOT NULL |  | —
body | TEXT | NOT NULL |  | — | Plaintext content
mood | TEXT | NULL |  | — | Happy¦Motivated¦Challenged¦Neutral
tags | TEXT | NULL |  | — | JSON array string
is_private | INTEGER | NOT NULL |  | — | 0=public, 1=private
date | TEXT | NOT NULL |  | — | YYYY-MM-DD
created_at | TEXT | NOT NULL |  | —
updated_at | TEXT | NOT NULL |  | —
TABLE: SKILLS
Student skill inventory with self-rating.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
name | TEXT | NOT NULL |  | — | e.g. 'Flutter'
category | TEXT | NOT NULL |  | — | Technical¦Soft Skill¦Language¦Tool
rating | INTEGER | NOT NULL |  | — | 1–5 scale
last_used | TEXT | NULL |  | — | YYYY-MM-DD
created_at | TEXT | NOT NULL |  | —
TABLE: RESUMES
Saved resume drafts.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
template_id | INTEGER | NOT NULL |  | — | 1=Simple 2=Pro 3=Modern
custom_sections | TEXT | NULL |  | — | JSON config
summary_override | TEXT | NULL |  | — | User-edited summary
is_default | INTEGER | NOT NULL |  | — | 1=default draft
generated_at | TEXT | NOT NULL |  | — | Last generated
TABLE: EXPORT_HISTORY
Log of all PDF exports.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
export_type | TEXT | NOT NULL |  | — | resume¦portfolio
template_id | INTEGER | NULL |  | — | 1–3 for resume
file_path | TEXT | NOT NULL |  | — | Saved export path
exported_at | TEXT | NOT NULL |  | — | ISO 8601
TABLE: AUDIT_LOG
Admin-only security log.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NULL | FK | users.id | SET NULL
action | TEXT | NOT NULL |  | — | login¦logout¦pin_fail¦admin_*
target | TEXT | NULL |  | — | Affected entity
timestamp | TEXT | NOT NULL |  | — | ISO 8601
ip_note | TEXT | NULL |  | — | Device model note

## 🗂 Flutter Scaffold
Flutter Project Folder & File Scaffold
Mark creates ALL files in Sprint 1 as placeholders. This locks architecture and prevents import chaos.
File Path | Sprint | Owner | Purpose
lib/main.dart | S1 | Mark | Entry point — runApp(). Zero business logic.
lib/app.dart | S1 | Mark | MaterialApp.router with GoRouter, ThemeData, top-level providers.
lib/config/app_constants.dart | S1 | Mark | ALL magic values: colors, paddings, font sizes, DB name/version.
lib/config/app_theme.dart | S1 | Mark | ThemeData light + dark. Material 3 brand colors.
lib/config/app_router.dart | S1 | Mark | GoRouter config with ALL named routes and auth redirect guards.
lib/models/user_model.dart | S1 | Mark | UserModel: fromMap(), toMap(), copyWith(). Immutable.
lib/models/project_model.dart | S3 | Mark | ProjectModel with imageUrls as List<String>.
lib/models/achievement_model.dart | S5 | Mark | AchievementModel with type enum.
lib/models/certificate_model.dart | S4 | Mark | CertificateModel with filePath for scans.
lib/models/reflection_model.dart | S5 | Mark | ReflectionModel with isPrivate bool.
lib/models/skill_model.dart | S4 | Mark | SkillModel with rating 1–5 and category.
lib/models/resume_model.dart | S6 | Mark | ResumeModel with templateId and customSections.
lib/models/export_history_model.dart | S6 | Mark | ExportHistoryModel for audit log.
lib/services/database_service.dart | S1 | Mark | Singleton. open(), close(), getDatabase(), migrations.
lib/services/auth_service.dart | S2 | Mark | register(), login(), logout(). SHA-256 hashing.
lib/services/profile_service.dart | S2 | Mark | getProfile(), updateProfile(). Separate from auth (SRP).
lib/services/project_service.dart | S3 | Mark | Full CRUD + search. Parameterized SQL only.
lib/services/image_storage_service.dart | S3 | Mark | saveImage(), deleteImage(), compressImage(). Max 500KB.
lib/services/achievement_service.dart | S5 | Mark | Full CRUD mirroring ProjectService pattern.
lib/services/certificate_service.dart | S4 | Mark | Full CRUD + filterByType().
lib/services/reflection_service.dart | S5 | Mark | Full CRUD + searchByBody() (LIKE).
lib/services/skill_service.dart | S4 | Mark | Full CRUD + sortByRating().
lib/services/resume_data_service.dart | S6 | Mark | mapPortfolioToResumeData(userId).
lib/services/pdf_service.dart | S6 | Mark | generateResumePdf(). TTF font registration.
lib/services/sync_service.dart | S7 | Mark | SQLite ↔ Firestore sync. Conflict resolution.
lib/services/backup_service.dart | S7 | Mark | exportDatabase(), importDatabase().
lib/services/security_service.dart | S7 | Mark | hashPin(), verifyPin(), PIN lock.
lib/providers/auth_provider.dart | S2 | Mark | ChangeNotifier: authState, currentUser, isLoading.
lib/providers/profile_provider.dart | S2 | Mark | Exposes userProfile; calls ProfileService.
lib/providers/project_provider.dart | S3 | Mark | Projects list, loading state; refresh after CRUD.
lib/providers/achievement_provider.dart | S5 | Mark | Mirror of ProjectProvider pattern.
lib/providers/certificate_provider.dart | S4 | Mark | Exposes filteredList by type.
lib/providers/reflection_provider.dart | S5 | Mark | Search results + isPrivate filter.
lib/providers/skill_provider.dart | S4 | Mark | Skills sorted by rating.
lib/providers/resume_provider.dart | S6 | Mark | selectedTemplate, resumeData, dirtyState.
lib/screens/splash_screen.dart | S1 | Mark | Logo + loading. Session check → redirect.
lib/screens/auth/login_screen.dart | S2 | Mark | Email + password form. Calls AuthProvider.login().
lib/screens/auth/register_screen.dart | S2 | Mark | Full registration form with validation.
lib/screens/home/dashboard_screen.dart | S2 | Mark | Stats overview + recent entries + FAB.
lib/screens/profile/profile_setup_screen.dart | S2 | Mark | Avatar + bio + school + course setup.
lib/screens/portfolio/projects_list_screen.dart | S3 | Mark | ListView.builder + search + filter chips.
lib/screens/portfolio/add_edit_project_screen.dart | S3 | Mark | Add/edit form; null = add mode.
lib/screens/portfolio/project_detail_screen.dart | S3 | Mark | Full view + image carousel + edit/delete.
lib/screens/portfolio/certificates_screen.dart | S4 | Mark | Certificates list + filter tabs + upload.
lib/screens/portfolio/achievements_screen.dart | S5 | Mark | Achievements list + add/edit.
lib/screens/portfolio/reflections_screen.dart | S5 | Mark | Reflections list + editor.
lib/screens/portfolio/skills_screen.dart | S4 | Mark | Skills tracker with animated progress bars.
lib/screens/portfolio/portfolio_overview_screen.dart | S5 | Mark | Aggregate: counts + recent from all modules.
lib/screens/resume/template_selection_screen.dart | S6 | Mark | 3 template preview cards.
lib/screens/resume/resume_builder_screen.dart | S6 | Mark | Live preview + section toggles + inline edits.
lib/screens/export/pdf_export_screen.dart | S6 | Mark | PDF preview + save to Downloads + share.
lib/screens/admin/admin_dashboard_screen.dart | S7 | Mark | Aggregate stats read from SQLite.
lib/screens/admin/admin_user_list_screen.dart | S7 | Mark | All students + search + portfolio count.
lib/screens/settings/security_screen.dart | S7 | Mark | PIN setup + lock screen.
lib/widgets/portfolio_card.dart | S3 | Mark | Reusable card for all portfolio items.
lib/widgets/image_carousel.dart | S3 | Mark | PageView-based carousel for images.
lib/widgets/empty_state_widget.dart | S3 | Mark | SVG + message for empty lists.
lib/widgets/loading_widget.dart | S3 | Mark | CircularProgressIndicator + message.
lib/widgets/tag_chip.dart | S3 | Mark | Colorized chips for tags/categories.
lib/widgets/skill_bar.dart | S4 | Mark | AnimatedContainer progress bar (1-5).
lib/widgets/resume_template_simple.dart | S6 | Mark | PH government/academic resume layout.
lib/widgets/resume_template_professional.dart | S6 | Mark | PH corporate resume layout.
lib/widgets/resume_template_modern.dart | S6 | Mark | Two-column fresh grad tech style.
lib/widgets/skeleton_loader.dart | S8 | Mark | Shimmer skeleton for loading states.
lib/utils/validators.dart | S2 | Mark | validateEmail(), validatePassword(), validateRequired().
lib/utils/date_formatter.dart | S2 | Mark | formatDate(), parseDate(), toISO8601().
lib/utils/file_utils.dart | S3 | Mark | getLocalPath(), generateUniqueFilename().
lib/utils/pdf_utils.dart | S6 | Mark | registerFonts(), buildPdfHeader() helpers.
💡 Sprint 1: Mark creates ALL files above as empty placeholders. Locks architecture, prevents spaghetti imports.

## ✅ Day 1 Checklist
Sprint 1 — Day 1 Kickoff Checklist
Mark completes rows 1-10 on Day 1. Tom + Rex work on their assigned items independently.
✓ | Task | Owner | Time | Done When
[ ] | Install Flutter SDK (stable) + Android Studio | Mark | 30m | flutter doctor shows no errors
[ ] | flutter create portfolioph --org com.portfolioph | Mark | 5m | Default counter app runs on emulator
[ ] | Add ALL packages to pubspec.yaml (see Tech Stack) | Mark | 10m | flutter pub get succeeds with 0 errors
[ ] | Delete counter app code; create empty MaterialApp scaffold | Mark | 5m | Clean main.dart with only MaterialApp
[ ] | Create full folder structure (see Flutter Scaffold) | Mark | 15m | All folders + placeholder .dart files exist
[ ] | app_constants.dart: colors, DB name, version | Mark | 15m | AppConstants class compiles
[ ] | database_service.dart: open() + create 10 tables | Mark | 30m | DB opens with all tables on fresh install
[ ] | app_router.dart: GoRouter with 3+ placeholder routes | Mark | 15m | App navigates between blank screens
[ ] | app_theme.dart: Material 3 brand colors | Mark | 15m | ThemeData applied to app
[ ] | splash_screen.dart: logo + loading + redirect | Mark | 15m | Splash shows then navigates
[ ] | Git init + push to GitHub | Mark | 10m | Remote repo visible; all members clone
[ ] | Android manifest: storage + camera permissions | Mark | 10m | Permissions declared in manifest
[ ] | Run app on physical Android device | Mark | 10m | App launches without crashes
[ ] | Research PH CV formats — collect 5+ examples | Tom | 2h | Examples saved in shared Drive folder
[ ] | Create low-fi wireframe sketches for 5 main tabs | Tom | 2h | Sketches reviewed by Mark
[ ] | Create project proposal document (LNU format) | Rex | 2h | Proposal draft in Google Docs
[ ] | Write README.md: project overview + team + setup | Rex | 1h | README pushed to GitHub
[ ] | Set up shared Google Drive + group chat | Rex | 30m | Drive folders created; chat pinned
★ Mark: ~3 hrs coding on Day 1 ¦ Tom: 4 hrs research/mockups ¦ Rex: 3.5 hrs docs/setup

## 📈 Metrics
Success Metrics & KPI Scorecard
Mark tracks these weekly. Tom/Rex update testing + docs KPIs.
KPI | Target | Measurement | Check Sprint | Actual | Status
Mark's total developer hours | 256 hrs |  | Every sprint | 0 | Not Started
Team total support hours | 107 hrs |  | Every sprint | 0 | Not Started
App crash rate (manual QA) | 0 critical crashes | Manual test log by Tom | S8 | — | Not Started
PDF export success rate | 100% on 2 devices | Tom tests on 2 phones × 3 templates | S6, S8 | — | Not Started
Screens implemented | ≥ 22 screens | Count .dart files in screens/ | S8 | 0 | Not Started
Unit test coverage (services) | ≥ 80% | flutter test --coverage | S8 | 0% | Not Started
Release APK size | < 50 MB | flutter build apk --analyze-size | S8 | — | Not Started
Weekly sprint deliverables completed | 8 / 8 | Demo log in Master Tracker | S8 | 0/8 | Not Started
Android API support range | API 26 → API 34 | Test on 2 physical devices | S8 | — | Not Started
Capstone paper chapters done | 5 / 5 chapters | Rex tracks in Google Docs | S8 | 0/5 | Not Started
SQLite query performance | All queries < 50 ms | Flutter DevTools profiling | S8 | — | Not Started
UI frame rate | 60 fps mid-range Android | Flutter performance overlay | S6, S8 | — | Not Started
Firebase sync success rate | 100% on stable connection | Manual test: offline → online | S7 | — | Not Started
DB backup/restore integrity | 100% data intact | Backup → wipe → restore → verify | S7 | — | Not Started
Presentation slides ready | 15-20 slides | Rex delivers final deck | S8 | 0 | Not Started
📌 Update 'Actual' column every week. Status: Not Started → In Progress → On Track / At Risk / Done